## Pivot table
Row Labels | Sum of Progress | Row Labels | Sum of Days Required | Project Name | Task Name | Progress
Consulting | 0.6 | Consulting | 92 | Consulting | Client Advisory | 0%
Customer Svc | 2 | Customer Svc | 77 |  | Market Expansion | 0%
Development | 1 | Development | 100 |  | Strategic Planning | 60%
Engineering | 0.2 | Engineering | 74 | Customer Svc | Customer Feedback | 0%
Events | 0.3 | Events | 80 |  | Service Improvement | 100%
Financial | 1.88 | Financial | 68 |  | Ticket Resolution | 100%
Logistics | 1.5 | Logistics | 75 | Development | Code Review | 0%
Marketing | 2.23 | Marketing | 74 |  | Feature Enhancement | 0%
Operations | 0.4 | Operations | 75 |  | Software Development | 100%
Product Dev | 1.78 | Product Dev | 53 | Engineering | Product Design | 20%
Production | 0.3 | Production | 96 |  | Prototype Testing | 0%
Research | 0.5 | Research | 82 |  | System Integration | 0%
Sales | 1.48 | Sales | 115 | Events | Conference Management | 0%
Support | 2 | Support | 78 |  | Event Planning | 30%
Training | 0.8 | Training | 79 |  | Sponsorship Coordinatio | 0%
Grand Total | 16.97 | Grand Total | 1218 | Financial | Budget Analysis | 10%
[5 empty] | Financial Reporting | 78%
[5 empty] | Investment Planning | 100%
|  |  |  | Logistics | Inventory Optimization | 0%
[5 empty] | Supply Chain Management | 50%
[5 empty] | Transportation Planning | 100%
|  |  |  | Marketing | Campaign Analysis | 0%
[5 empty] | Content Creation | 100%
[5 empty] | Market Research | 78%
[5 empty] | Social Media Planning | 45%
|  |  |  | Operations | Facility Maintenance | 0%
[5 empty] | Inventory Management | 0%
[5 empty] | Process Optimization | 40%
|  |  |  | Product Dev | Prototype Development | 100%
[5 empty] | Quality Assurance | 78%
[5 empty] | User Interface Design | 0%
|  |  |  | Production | Manufacturing | 30%
[5 empty] | Packaging Design | 0%
[5 empty] | Quality Control | 0%
|  |  |  | Research | Data Collection | 0%
[5 empty] | Market Trends Analysis | 50%
[5 empty] | Research Paper Writing | 0%
|  |  |  | Sales | Client Meetings | 78%
[5 empty] | Contract Negotiation | 0%
[5 empty] | Lead Generation | 70%
|  |  |  | Support | Bug Fixes | 100%
[5 empty] | Software Updates | 0%
[5 empty] | Technical Support | 100%
|  |  |  | Training | Certification Programs | 0%
[5 empty] | Employee Training | 80%
[5 empty] | Skill Development | 0%
Grand Total

## Project Management Data
[7 empty] | Staus | Count
Excel Sample Data | [6 empty] | Complete | 9
[7 empty] | In Progress | 15
Project Management Data | [6 empty] | Not started | 22
Project Name | Task Name | Assigned to | Start Date | Days Required | End Date | Progress
Marketing | Market Research | Alice | 2024-01-01 | 13 | 2024-01-14 | 78%
Marketing | Content Creation | Bob | 2024-01-14 | 14 | 2024-01-28 | 100%
Marketing | Social Media Planning | Charlie | 2024-01-28 | 22 | 2024-02-19 | 45%
Marketing | Campaign Analysis | Daisy | 2024-02-18 | 25 | 2024-03-14 | 0%
Product Dev | Prototype Development | Ethan | 2024-01-02 | 18 | 2024-01-20 | 100%
Product Dev | Quality Assurance | Fiona | 2024-01-20 | 10 | 2024-01-30 | 78%
Product Dev | User Interface Design | Gabriel | 2024-02-04 | 25 | 2024-02-29 | 0%
Customer Svc | Service Improvement | Hannah | 2024-02-01 | 22 | 2024-02-23 | 100%
Customer Svc | Ticket Resolution | Ian | 2024-02-24 | 25 | 2024-03-20 | 100%
Customer Svc | Customer Feedback | Julia | 2024-03-21 | 30 | 2024-04-20 | 0%
Financial | Budget Analysis | Kevin | 2024-02-02 | 22 | 2024-02-24 | 10%
Financial | Financial Reporting | Mark | 2024-02-13 | 21 | 2024-02-09 | 78%
Financial | Investment Planning | Mark | 2024-03-19 | 25 | 2024-04-13 | 100%
Research | Market Trends Analysis | Nathan | 2024-01-02 | 23 | 2024-01-25 | 50%
Research | Data Collection | Olivia | 2024-01-26 | 32 | 2024-02-27 | 0%
Research | Research Paper Writing | Peter | 2024-02-28 | 27 | 2024-03-26 | 0%
Development | Software Development | Quinn | 2024-01-02 | 36 | 2024-02-07 | 100%
Development | Feature Enhancement | Rachel | 2024-02-08 | 34 | 2024-03-13 | 0%
Development | Code Review | Sam | 2024-03-14 | 30 | 2024-04-13 | 0%
Production | Manufacturing | Tim | 2024-01-03 | 47 | 2024-02-19 | 30%
Production | Quality Control | Ursula | 2024-02-17 | 27 | 2024-03-15 | 0%
Production | Packaging Design | Victor | 2024-03-14 | 22 | 2024-04-05 | 0%
Sales | Lead Generation | Wendy | 2024-01-03 | 60 | 2024-03-03 | 70%
Sales | Client Meetings | Xavier | 2024-01-06 | 20 | 2024-01-26 | 78%
Sales | Contract Negotiation | Yvette | 2024-02-03 | 35 | 2024-03-09 | 0%
Support | Technical Support | Zoe | 2024-01-01 | 25 | 2024-01-26 | 100%
Support | Bug Fixes | Aaron | 2024-01-27 | 31 | 2024-02-27 | 100%
Support | Software Updates | Bella | 2024-03-02 | 22 | 2024-03-24 | 0%
Operations | Process Optimization | Calvin | 2024-01-03 | 30 | 2024-02-02 | 40%
Operations | Inventory Management | Diane | 2024-02-03 | 25 | 2024-02-28 | 0%
Operations | Facility Maintenance | Edward | 2024-02-29 | 20 | 2024-03-20 | 0%
Consulting | Strategic Planning | Fiona | 2024-01-02 | 35 | 2024-02-06 | 60%
Consulting | Market Expansion | Gary | 2024-02-02 | 32 | 2024-03-05 | 0%
Consulting | Client Advisory | Helen | 2024-03-06 | 25 | 2024-03-31 | 0%
Training | Employee Training | Isaac | 2024-01-04 | 27 | 2024-01-31 | 80%
Training | Certification Programs | Jane | 2024-01-28 | 30 | 2024-02-27 | 0%
Training | Skill Development | Kyle | 2024-02-28 | 22 | 2024-03-21 | 0%
Events | Event Planning | Laura | 2024-01-03 | 25 | 2024-01-28 | 30%
Events | Conference Management | Mike | 2024-02-03 | 20 | 2024-02-23 | 0%
Events | Sponsorship Coordinatio | n Nancy | 2024-02-24 | 35 | 2024-03-30 | 0%
Logistics | Supply Chain Management | Oscar | 2024-01-03 | 25 | 2024-01-28 | 50%
Logistics | Transportation Planning | Patricia | 2024-01-29 | 30 | 2024-02-28 | 100%
Logistics | Inventory Optimization | Quentin | 2024-03-29 | 20 | 2024-04-18 | 0%
Engineering | Product Design | Rachel | 2024-01-02 | 25 | 2024-01-27 | 20%
Engineering | System Integration | Sam | 2024-02-02 | 22 | 2024-02-24 | 0%
Engineering | Prototype Testing | Tom | 2024-02-23 | 27 | 2024-03-21 | 0%

## Dashboard
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.
Project by days required and Progress